## Errata
Item | Board | Issue - Description | Details | Solution | Status
1 | SOM | Power selection for I2C level translator (U39) |  | D1 - DNI, D2 populated | Tested, to be implemented Rev B | done Rev B
2 | SOM | USB Phy Refclk needs to be referenced at 3.3V. Currently from 1.8V it's at the limit |  | Power Y2 oscilator from 3.3V | Tested, to be implemented Rev B | done Rev B
3 | SOM | 2 vias in the exposed copper region on the perimeter of the board will be shorted by the heatspreader (next to C868) |  | Remove them | To be implemented Rev B | done Rev B
4 | SOM | AD9542 clock generator configuration | Program EEprom by downloading the configuration from the AD9542. | Disconnect EEprom from Zynq and connect to the AD9542. DNI R562, R565, populate R563, R566 | Tested, to be implemented Rev B | done Rev B
|  |  | Enable Load from Eeprom at power-up | load R564 | Tested, to be implemented Rev B | done Rev B
5 | SOM | Power | GTH power - improve overshoot and undershoot at load step | add 470uF polymer Cap to the output of both MGTAVTT and MGTAVCC | Tested, to be implemented Rev B | done Rev B
|  |  | VCCINT PL power - improve overshoot and undershoot at load step | current schematic yields best results
6 | SOM | parts with wrong footprint on PCB |  | fix footprint in layout | to be implemented Rev B | done Rev B
7 |  | different caps loaded due to availability |  | capacitor availability did improve, no footprint changes
8 | SOM | enable HMC7044 CML outputs (less noise, force to logic 0 for SYSREF pulses) |  | Add external termination resistors for DC -coupled outputs | Tested on HMC7044 ev board, to be implemented Rev B | done Rev B
9 | SOM + Carrier | Move TCXO from carrier to SOM |  | add TCXO on the SOM, connect to CLKIN3 with 0 Ohm resistors | to be implemented Rev B | done Rev B
10 | SOM | Reduce crosstalk, noise |  | Place via stitching to GND on the pads for the shields, both top and bottom and perimeter of the board | to be implemented Rev B | done Rev B
11 | SOM | Add two extra mounting holes on the edge |  |  | To be implemented Rev B | done Rev B
12 | SOM | Connect all mounting holes to GND |  |  | To be implemented Rev B
13 | SOM | Move passive components away from edge 0.5 … 1mm if possible |  | Move R334, R332, R337, C630, C626, C177, C675 etc. | To be implemented Rev B | done Rev B
14 | SOM | replaced the Temp sensor with TMP36GRTZ | AD590JCPZ accuracy is bad. Not enough output current | replace with TMP36GRTZ | to be implemented Rev B | done Rev B
15 | SOM | SYNC_HMC7044 should arrive in the FPGA | SYNC_HMC7044 needs to be level translated from 3.3V to 1.8V | Use resistor divider. Modify R110 200 Ohm and R114 249 Ohm | Tested - Resistor divider adds delays. Will be doen only if necessary.
16 | SOM | difficult to solder shields |  | modify pads for shields to expose only the solder pads | To be implemented Rev B | done Rev B
1 | Carrier | USB type C | switching roles in DRP mode | provide jumpers to connect USB_ID and USB_OTG_CPEN either to USB3320C phy or MIO pins. Connect Interrupt pin from PTN5150 to MIO. | Tested, to be implemented Rev B | done Rev B
|  |  |  | modify R212 1K instead of 10K | Tested, to be implemented Rev B | done Rev B
|  |  | USB3 lines not working | add AC coupling to USB3_GTR_TX_P/N | Tested, to be implemented Rev B | done Rev B
|  |  | PTN5150A is not reporting correct connection status each time | VBUS needs to be turned off by driver when disconnecting the USB device
|  |  | PG_ALL goes low and the SOM+carrier turn off when attaching some USB C to type A adapters. | Add an RC delay when sensing 5V. | To be implemented in Rev B | done Rev B
on Rev A PCBs attach adapter before powering the Boards
2 | Carrier | SOM SD card can not be removed while it's inserted in the carrier; P13 and P4 are in the way |  | Move P13, M4, P3 to the left | to be implemented Rev B | done Rev B
3 | Carrier | UART - USB bridge issues | Serial port doesn't come up every time. Currently CP2104 is loaded. Schematic not compatible with CP2102 (need divider on VBUS pin) | Replace with FTDI FT232R | to be implemented Rev B | done Rev B
4 | Carrier | Board turns off when conencting FMC card |  | Disconnect from GND pin K40 from FMC conenctor (P1). Leave floating | Tested, to be implemented Rev B | done Rev B
5 | Carrier | enable HMC7044 CML outputs (less noise, force to logic 0 for SYSREF pulses) |  | No Hardware changes. All clock outputs are AC-coupled
6 | Carrier | silkscreen issues |  | J6, J5: remove "1pps" | to be implemented Rev B | done Rev B
|  |  |  | P2: "Displayport" instead of "HDMI OUT" | to be implemented Rev B | done Rev B
7 | Carrier | Fan PWM is not working at max frequency | falling edge is too slow | Drive Q1 gate from 3.3V. There is a spare 1V8 to 3V3 translator input (U21). | to be implemented Rev B | done Rev B
8 | Carrier | Placement for mode switches |  | Change switch order (mode 3 -> mode 0). Rotate 180 deg. | to be implemented Rev B | done Rev B
9 | Carrier | AD9545 possibility to load AD9545 boot at startup |  | Add EEPROM, pull-up resistor to M3 | to be implemented Rev B | done Rev B
10 | Carrier | When insterted in a PCIE case the power cable won't fit |  | Rotate power connector 90 deg | to be implemented Rev B | done Rev B
11 | Carrier | USB load switch protection |  | Use NXP5P3090 power switch ( DNI the current one and load the new in parallel) | to be implemented Rev B | done Rev B
12 | Carrier | connect all unused IOs from the PL to a header |  |  | to be implemented Rev B | done Rev B
13 | Carrier | Add two extra mounting holes |  |  | to be implemented Rev B | done Rev B
14 | SOM + Carrier | Move TCXO from carrier to SOM |  | DNI SOM TCXO on carrier | to be implemented Rev B | done Rev B
15 | Carrier | ADM1266 can't output active low on fault signals | turn on DS12 and DS13 with '1' logic | remove Q25 and Q26. Add DNI option for pull-up resistors to 12V0 on PWR_FAULT1/2 signals to keep LEDs turned on after a fault event (In this case DNI R127, R129 on SOM) Also turn LEDs on from 12V0, modify R263, R264 to 1.2K. | to be implemented Rev B | done Rev B